## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US-01 | Create applicant account | As a TA applicant, I want to create an account on the platform, So that I can access vacancies and submit applications online instead of relying on email. | High | 1 | 1. A TA applicant can register with basic personal details. 2. The system confirms successful registration. 3. The applicant can log in with the created account. | 3 | Stakeholder: TA ¦ Epic: Applicant onboarding ¦ Solves: no fixed recruitment system; scattered email process.
US-02 | Maintain reusable applicant profile | As a TA applicant, I want to save and update my personal information, skills, and CV, So that I do not need to fill in the same details every semester. | High | 1 | 1. The applicant can enter and edit personal information. 2. The applicant can upload or replace a CV. 3. Saved profile data can be reused for future applications. | 5 | Stakeholder: TA ¦ Epic: Applicant profile management ¦ Solves: repetitive and redundant form filling.
US-03 | Browse all TA vacancies | As a TA applicant, I want to view all available TA vacancies in one place, So that I can compare opportunities without searching through separate emails. | High | 1 | 1. The platform shows a list of all open TA vacancies. 2. Each vacancy displays the module title and current recruitment status. 3. Closed or filled vacancies are clearly marked or hidden. | 3 | Stakeholder: TA ¦ Epic: Vacancy discovery ¦ Solves: applicants cannot centrally view all available posts.
US-04 | View vacancy details | As a TA applicant, I want to view detailed vacancy information, So that I can understand the required skills, working hours, duties, and pay before applying. | High | 1 | 1. Each vacancy includes module name, number of posts, pay, duties, weekly workload, and required skills. 2. The applicant can open a details page from the vacancy list. 3. Information is clearly displayed before application submission. | 2 | Stakeholder: TA ¦ Epic: Vacancy discovery ¦ Solves: lack of transparency about job requirements.
US-05 | Submit application with skill declaration | As a TA applicant, I want to apply for a vacancy by selecting the skills I already have and attaching my CV, So that the system can assess whether I meet the vacancy requirements. | High | 1 | 1. The applicant can submit an application for an open vacancy. 2. The applicant can declare possessed skills from a list. 3. The system stores the application together with the applicant profile and CV. | 5 | Stakeholder: TA ¦ Epic: Application submission ¦ Solves: inefficient email submission and unclear skill matching.
US-06 | Track application status | As a TA applicant, I want to track the status of each application, So that I know whether it is submitted, viewed, accepted, rejected, or no longer available. | High | 1 | 1. The applicant can see all submitted applications on a dashboard. 2. Each application displays a current status. 3. Status updates are shown after MO review actions or when a vacancy is filled. | 3 | Stakeholder: TA ¦ Epic: Application tracking ¦ Solves: applicants cannot know whether they are being considered or whether posts are full.
US-07 | Publish TA vacancies | As a Module Organiser (MO), I want to create and publish a TA vacancy with clear requirements, So that qualified applicants can understand exactly what the role requires. | High | 1 | 1. The MO can enter module name, number of posts, pay, duties, weekly hours, and required skills. 2. The vacancy can be published online. 3. Published vacancies appear to applicants in the vacancy list. | 5 | Stakeholder: MO ¦ Epic: Vacancy management ¦ Solves: lack of structured vacancy information in email-based recruitment.
US-08 | View applications in one dashboard | As a Module Organiser (MO), I want to review all applications for a vacancy in one place, So that I do not need to read and manage large volumes of recruitment emails manually. | High | 1 | 1. The MO can open a vacancy and see all related applications in one dashboard. 2. Each application shows applicant name, submitted CV, and declared skills. 3. The list is accessible without using external email threads. | 5 | Stakeholder: MO ¦ Epic: Candidate review ¦ Solves: screening is complex and cumbersome because MOs need to read many emails.
US-09 | Auto-shortlist fully matched applicants | As a Module Organiser (MO), I want the system to automatically shortlist applicants whose skills fully match the vacancy requirements, So that I can identify suitable candidates faster. | High | 1 | 1. The system compares declared applicant skills with the vacancy requirement list. 2. Fully matched applicants are shown in the default shortlist. 3. Non-matching applicants are separated from the default shortlist. | 8 | Stakeholder: MO ¦ Epic: Candidate filtering ¦ Solves: MOs may not be able to tell whether an applicant meets the skill requirements.
US-10 | Review filtered applicants with missing-skill labels | As a Module Organiser (MO), I want to view filtered applicants together with the skills they are missing, So that I can still consider them when there are not enough fully qualified candidates. | Medium | 1 | 1. The MO can access a separate list of filtered applicants. 2. Missing skills are clearly labelled for each applicant. 3. The MO can still open the applicant's profile and CV before making a decision. | 5 | Stakeholder: MO ¦ Epic: Candidate filtering ¦ Solves: flexible review when fully matched applicants are insufficient.
US-11 | Make online hiring decisions | As a Module Organiser (MO), I want to accept or reject applicants online, So that I can complete TA recruitment efficiently and keep applicants informed through the system. | High | 1 | 1. The MO can mark an application as accepted or rejected. 2. The applicant status updates immediately after the decision. 3. Accepted hires reduce the remaining available posts for the vacancy. | 5 | Stakeholder: MO ¦ Epic: Hiring decision ¦ Solves: inefficient manual communication and delayed status updates.
US-12 | Monitor total TA workload | As the system, I want to monitor the total allocated workload of each TA across roles, So that overloaded applicants can be flagged and intervention can be triggered when necessary. | Medium | 1 | 1. The system calculates the total weekly working hours allocated to each TA. 2. The system flags a TA whose total workload exceeds a defined threshold. 3. The MO can see the overload warning before finalising allocation. | 8 | Stakeholder: System/MO ¦ Epic: Allocation control ¦ Solves: risk of overloading TAs across multiple assignments.